## Savings Detail
[8 empty] | Affects Project ROI? | [5 empty] | Potential Savings Extensions
Benefit/Savings Description | Project Savings Category | Budget Category/Funding Source | Unit Desc | Units | Rate per Unit | Total Savings | Annual Multiplier | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Savings Categories | Unit Desc Entries
Cost savings/avoidance from better tracking and monitoring of historical vendor performance, enhanced competitive bidding, proactive contract/vendor performance monitoring, improved vendor selection processes, and enhanced encumbrance/budget controls (1) | Cost Avoidance |  | ANN | 1 | 1000000 | 1000000 | 1.4 |  |  | x | x | x | x |  |  | 980000 | 2744000 | 3841600 | 5378240
Time and Labor module re-development costs that would be incurred if PS is not implemented; includes estimated annual support costs | Cost Avoidance |  | EA | 1 | 1253200 | 1253200 | 0.1 | x | x | x | x | x | x | 1253200 | 125320 | 137852 | 151637.2 | 166800.92 | 183481.012 | Cost Avoidance | EA
Avoidance of postage and pre-printed forms costs by using the Portal to deliver information and forms | Tangible Benefit |  | ANN | 1 | 20000 | 20000 | 1.03 |  | x | x | x | x | x |  | 20600 | 21218 | 21854.54 | 22510.1762 | 23185.4815 |  | HR
Staff time reallocation due to efficiency enhancements via real-time remote access to data; enhanced access to more helpful data on-line; reports viewable on-line locally, real-time; elimination of Peachtree and other "Shadow Systems" and processes; automatic bookings/reversals/ adjustments; historical data reporting; multiple payments consolidation; interfaces with user-department systems to eliminate duplicative data entry and/or report preparation time | Cost Avoidance |  |  | 13460 | 34 | 457640 | 1.03 |  |  | x | x | x | x |  |  | 485510.276 | 500075.5843 | 515077.8518 | 530530.1874
Reduction in Travel (MB) reimbursement/advances and check processing costs | Tangible Benefit |  | ANN | 1 | 32000 | 32000 | 1.03 |  |  | x | x | x | x |  |  | 33948.8 | 34967.264 | 36016.2819 | 37096.7704
Reallocation of staff time from Portal/SSO administration (set-up/security admin., web development, self-service of staff, help desk calls, disk storage) and constituent servicing | Cost Avoidance |  |  | 4160 | 34 | 141440 | 1.03 |  | x | x | x | x | x |  | 145683.2 | 150053.696 | 154555.3069 | 159191.9661 | 163967.7251
Savings of incremental cost from licensing a different financial system (illustrative of the exceptional licensing agreement with PeopleSoft) | Cost Avoidance |  | EA | 1 | 500000 | 500000 | 1 | Affects Project ROI? Y3: x; Potential Savings Extensions Y3: 500010
Savings of incremental annual support cost from licensing a different financial system (illustrative of the exceptional licensing agreement with PeopleSoft) | Cost Avoidance |  | ANN | 1 | 100000 | 100000 | 1.05 |  |  | x | x | x | x |  |  | 105000 | 105000 | 105000 | 105000
Elimination of KPMG Performance Series annual maintenance costs | Tangible Benefit |  | ANN | 1 | 255760 | 255760 | 1.05 |  |  | x | x | x | x |  |  | 281975.4 | 296074.17 | 310877.8785 | 326421.7724
Elimination of KPMG/Tier Professional Services |  |  |  | 1 | 50000 | 50000 | 1.05 |  |  | x | x | x | x |  |  | 55125 | 57881.25 | 60775.3125 | 63814.0781
Staff time reallocation due to Personnel Self-Service / Workflow | Cost Avoidance |  | HR | 1377 | 33.6538 | 46341.3462 | 1.03 |  | x | x | x | x | x |  | 47731.5865 | 49163.5341 | 50638.4402 | 52157.5934 | 53722.3212
Intangibles:
Customer service responsiveness improvement | Tangible Benefit
Total | [5 empty] | 2856381.3462 |  | Potential Savings Extensions Y1: 1253200; Potential Savings Extensions Y2: 339334.7865; Potential Savings Extensions Y3: 2799856.7062; Potential Savings Extensions Y4: 4116683.7553; Potential Savings Extensions Y5: 5270007.9804; Potential Savings Extensions Y6: 6865459.348
Cumulative Total | [5 empty] | 20644542.5764 |  | Potential Savings Extensions Y1: 1253200; Potential Savings Extensions Y2: 1592534.7865; Potential Savings Extensions Y3: 4392391.4927; Potential Savings Extensions Y4: 8509075.248; Potential Savings Extensions Y5: 13779083.2284; Potential Savings Extensions Y6: 20644542.5764
(1) - Enhanced supply chain management is expected from: 1. Increasing number of bidders and bidding out more purchases via use of Web; 2. Expediting RFP/bid process; 3. E-catalog use for purchasing by departments with pre-approved and negotiated prices; 4. proactive vendor management using statistical analysis to "weed out" costly/poor performing vendors; 5. early payment discount capturing; 6. volume discount capturing via accurate analysis of county-wide purchases and selective re-negotiating with vendors; 7. trend/market fluctuation analysis to but the "right amount at the right time" | [5 empty] | 0
0

## Savings Summary
| Benefit/Savings Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Total
Tangible Benefit:
Tangible Benefits Subtotal:
Cost Avoidance:
|  | 1253200 | 339334.7865 | 2799856.7062 | 4116683.7553 | 5270007.9804 | 6865459.348 | 20644542.5764
| Cost Avoidance Subtotal: | 1253200 | 339334.7865 | 2799856.7062 | 4116683.7553 | 5270007.9804 | 6865459.348 | 20644542.5764 | 20644542.5764
Savings Total: |  | 1253200 | 339334.7865 | 2799856.7062 | 4116683.7553 | 5270007.9804 | 6865459.348 | 20644542.5764 | 20644542.5764

## MR Summary
Schedule 1: | Phase II | Phase II (Orig.) | % Change
Training of Staff on PeopleSoft System | 176000 | 330000 | -46.67%
PeopleSoft Software and Hardware | 1120362.6473 | 1217272.311 | -7.961%
Additional PeopleSoft Module Licenses | 246589 | 195411.6 | 26.19%
Project Manager | 51500 | 51500 | 0%
IT, Fiscal Services, and HR Staff Resources | 1334900 | 1203660.359 | 10.9%
Contingency | 742954.2565 | 674066.974 | 10.22%
Sub-Total: | 3672305.9038 | 3671911.2439 | 0.01075%
eVerge Professional Services | 2802622 | 2417475.7282 | 15.93%
Sub-Total: | 6474927.9038 | 6089386.9721 | 6.331%
-2000000
Less Phase I Unspent Fund Balance | -802990
Total: | 3671937.9038

## Cost Detail
[8 empty] | Affects Project ROI? | [5 empty] | Potential Cost Extensions
Cost Description | Project Cost Category | Budget Category/Funding Source | Unit Desc | Units | Rate per Unit | Total Cost | Annual Multiplier | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Cost Categories | Unit Desc Entries
Hardware/Software:
IT Hours - New Development, Phase I | Implementation Svcs |  | HRS | 2097.3333 | 122 | 255874.6667 |  | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 255874.6667 | Development Svcs | ANN
IT Hours - New Development, Phase II | Implementation Svcs |  | HRS | 8400 | 122 | 1024800 |  | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 1024800 | Development Svcs | ANN
IT Hours - New Development, Phase III | Implementation Svcs |  | HRS | 5500 | 122 | 671000 |  | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 671000 | Development Svcs | ANN
Modifications | Implementation Svcs |  | HRS | 350 | 122 | 42700 |  | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 42700 | Infrastructure
Third Party Interfaces/Integations | Implementation Svcs |  | HRS | 1 | 75000 | 75000 |  | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 75000 | Infrastructure
User Hours - PTNE/OT, Phase I | Implementation Svcs |  | HRS | 2200 | 33.6538 | 74038.4615 |  | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 74038.4615 | Infrastructure
User Hours - PTNE/OT, Phase II | Implementation Svcs |  | HRS | 7400 | 26 | 192400 |  | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 192400 | Infrastructure
User Hours - PTNE/OT, Phase III | Implementation Svcs |  | HRS | 2750 | 26.78 | 73645 |  | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 73645 | Infrastructure
Server and Oracle Software Licenses Acquisition - Phase I | Software |  | ANN | 1 | 108627.619 | 108627.619 | 1.0001 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 108627.619
Server and Oracle Software Licenses Maintenance - Phase I |  |  |  | 1 | 41197.1429 | 41197.1429 | 1.05 | x | x | x | x | x | x | 41197.1429 | 0
Server Hardware Acquisition - Phase I | Infrastructure |  | ANN | 1 | 365618.0952 | 365618.0952 | 1.0001 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 365618.0952
Server Hardware Maintenance - Phase I |  |  |  | 1 | 40133.3333 | 40133.3333 | 1.05 | x | x | x | x | x | x | 40133.3333 | 0
Server and Oracle Software Licenses Acquisition - Phase II | Software |  | ANN | 1 | 291525 | 291525 | 1.0001 | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 291554.1525
Server and Oracle Software Licenses Maintenance - Phase II |  |  |  | 1 | 52797 | 52797 | 1.05 | Affects Project ROI? Y2: x; Affects Project ROI? Y3: x; Affects Project ROI? Y4: x; Affects Project ROI? Y5: x; Affects Project ROI? Y6: x; Potential Cost Extensions Y2: 55436.85
Server Hardware Acquisition - Phase II | Infrastructure |  | ANN | 1 | 831448 | 831448 | 1.0001 | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 831531.1448
Server Hardware Maintenance - Phase II |  |  |  | 1 | 84110 | 84110 | 1.05 | Affects Project ROI? Y2: x; Affects Project ROI? Y3: x; Affects Project ROI? Y4: x; Affects Project ROI? Y5: x; Affects Project ROI? Y6: x; Potential Cost Extensions Y2: 88315.5
Server and Oracle Software Licenses Acquisition - Phase III | Software |  | ANN | 1 | 248578.0952 | 248578.0952 | 1.0001 | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 248627.8133
Server and Oracle Software Licenses Maintenance - Phase III |  |  |  | 1 | 28659.0476 | 28659.0476 | 1.05 | Affects Project ROI? Y3: x; Affects Project ROI? Y4: x; Affects Project ROI? Y5: x; Affects Project ROI? Y6: x; Potential Cost Extensions Y3: 31596.6
Server Hardware Acquisition - Phase III | Infrastructure |  | ANN | 1 | 594115.2381 | 594115.2381 | 1.0001 | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 594234.0671
Server Hardware Maintenance - Phase III |  |  |  | 1 | 59411.4286 | 59411.4286 | 1.05 | Affects Project ROI? Y3: x; Affects Project ROI? Y4: x; Affects Project ROI? Y5: x; Affects Project ROI? Y6: x; Potential Cost Extensions Y3: 65501.1
Hubs | Infrastructure | P&R | EA | 4 | 4850 | 19400 | 0.05 |  | x | x | x | x | x |  | 0 |  |  | 1122.8963 | 1179.0411
Hubs Maintenance | Infrastructure | P&R | EA | 4 | 485 | 1940 | 0.05 |  | x | x | x | x | x |  | 0 |  |  | 112.2896 | 117.9041
Communication Lines |  |  |  | 4 | 4800 | 19200 | 1.05 |  | x | x | x | x | x |  | 0 |  |  | 23337.72 | 24504.606
Additional PS Modules |  |  | EA | 1 | 153000 | 153000 | 1e-08 | Affects Project ROI? Y2: x; Affects Project ROI? Y3: x; Affects Project ROI? Y4: x; Potential Cost Extensions Y1: 40000; Potential Cost Extensions Y2: 205491; Potential Cost Extensions Y3: 459000; Potential Cost Extensions Y4: 0.00153
Annual Support for Additional PS Modules |  |  | EA | 1 | 30600 | 30600 | 1.05 | Affects Project ROI? Y2: x; Affects Project ROI? Y3: x; Affects Project ROI? Y4: x; Affects Project ROI? Y5: x; Affects Project ROI? Y6: x; Potential Cost Extensions Y2: 41098
Portal/SSO:
Contractor Professional Services |  |  | EA | 1 | 751000 | 751000 | 1 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 751000
Contractor Professional Services for Infrastructure - Phase I | Infrastructure |  | ANN | 1 | 70875 | 70875 | 0.1 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 70875
IT Hours - New Development |  |  | EA | 5886.6667 | 122 | 718173.3333 | 1.05 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 718173.3333
Training and Services:
PS Project Manager, Phase I | Other |  | ANN | 1 | 50000 | 50000 | 1.03 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 50000
PS Project Manager, Phase II | Other |  | ANN | 1 | 50000 | 50000 | 1.03 | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 51500
PS Project Manager, Phase III | Other |  | ANN | 1 | 50000 | 50000 | 1.03 | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 53045
Project Staff Training - Core Implementation Team, Phase I | Training |  | EA | 200 | 425 | 85000 | 1 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 85000
Project Staff Training - Core Implementation Team, Phase II | Training |  | EA | 400 | 400 | 160000 | 1 | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 160000
Project Staff Training - Core Implementation Team, Phase III | Training |  | EA | 300 | 425 | 127500 | 1 | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 127500
Travel Costs - Training, Phase I |  |  | EA | 1 | 8500 | 8500 | 1 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 8500
Travel Costs - Training, Phase II |  |  | EA | 1 | 16000 | 16000 | 1 | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 16000
Travel Costs - Training, Phase III |  |  | EA | 1 | 12750 | 12750 | 1 | Affects Project ROI? Y2: x; Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 12750
Contractor Professional Services - Implementation, Phase I | Other |  | EA | 1 | 1519417.4757 | 1519417.4757 | 0 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 1519417.4757
Contractor Professional Services - Implementation, Phase II | Other |  | EA | 1 | 2802622 | 2802622 | 1 | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 2802622
Contractor Professional Services - Implementation, Phase III | Other |  | EA | 1 | 3041390 | 3041390 | 1.0001 | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 3041998.3084
Annual Support for PS Financials |  |  | EA | 1 | 305000 | 305000 | 1.05 | Affects Project ROI? Y4: x; Affects Project ROI? Y5: x; Affects Project ROI? Y6: x; Potential Cost Extensions Y4: 353075.625; Potential Cost Extensions Y5: 370729.4062; Potential Cost Extensions Y6: 389265.8766
Contractor Professional Services - Post Go Live Support | Other |  | ANN | 1 | 100000 | 100000 | 1.05 | Affects Project ROI? Y4: x; Affects Project ROI? Y5: x; Affects Project ROI? Y6: x; Potential Cost Extensions Y4: 115762.5; Potential Cost Extensions Y5: 121550.625; Potential Cost Extensions Y6: 127628.1562
Contingency:
Phase I |  |  | ANN | 1 | 660782.9299 | 660782.9299 | 1 | Affects Project ROI? Y1: x; Potential Cost Extensions Y1: 660782.9299
Phase II |  |  | ANN | 1 | 596478.66 | 596478.66 | 1 | Affects Project ROI? Y2: x; Potential Cost Extensions Y2: 596479.2565
Phase III |  |  | ANN | 1 | 277629.179 | 277629.179 | 1 | Affects Project ROI? Y3: x; Potential Cost Extensions Y3: 277629.7343
Total | [5 empty] | 16782936.7062 |  | Potential Cost Extensions Y1: 4789238.0577; Potential Cost Extensions Y2: 6474927.9038; Potential Cost Extensions Y3: 5656527.6231; Potential Cost Extensions Y4: 468838.1265; Potential Cost Extensions Y5: 516852.9371; Potential Cost Extensions Y6: 542695.584
Cumulative Total | [5 empty] | 18449080.2322 |  | Potential Cost Extensions Y1: 4789238.0577; Potential Cost Extensions Y2: 11264165.9615; Potential Cost Extensions Y3: 16920693.5846; Potential Cost Extensions Y4: 17389531.7111; Potential Cost Extensions Y5: 17906384.6482; Potential Cost Extensions Y6: 18449080.2322
Contingency as a % of Year 1 Costs: | [5 empty] | 13.8% |  | Potential Cost Extensions Y1: 13.8%; Potential Cost Extensions Y2: 9.212%; Potential Cost Extensions Y3: 4.908%
Explanation of E-Financial System Implementation Resolution Costa and Funding |  |  |  |  | Phase I | Phase II | Phase III
Original Funding and Expenditures to Date:
MR#02043 Appropriation |  |  |  |  | 2900000
PeopleSoft Licenses |  |  |  |  | -1731324
Data Security/Single Sign-on Software and Hardware |  |  |  |  | -412764
System Selection and Due Diligence |  |  |  |  | -201690
Total Remaining Appropriation: |  |  |  |  | 554222
Projected Expenditures and Required Funding:
eVerge Professional Services |  |  |  |  | 1519417.4757 | 2802622 | 3041390
Data Security and Single Sign-on Implementation:
Accenture Professional Services |  |  |  |  | 751000
Hardware |  |  |  |  | 70875
IT, Fiscal Services, and HR Staff Resources |  |  |  |  | 718173.3333
Contingency |  |  |  |  | 437730.4167
Data Security Sub-Total of Hardware, Software, Staffing, and Contingency |  |  |  |  | 1977778.75
PeopleSoft Implementation:
PeopleSoft Software and Hardware |  |  |  |  | 555576.1905 | 1266837.6473 | 939959.5804
Training of Staff on PeopleSoft System |  |  |  |  | 93500 | 176000 | 140250
Additional PeopleSoft Module Licenses |  |  |  |  | 40000 | 194098 | 459000
IT, Fiscal Services, and HR Staff Resources |  |  |  |  | 329913.1282 | 1217200 | 744645
Project Manager |  |  |  |  | 50000 | 51500 | 53045
Contingency |  |  |  |  | 223052.5133 | 596478.66 | 277629.179
PeopleSoft Annual Support |  |  |  |  | - 0 - | - 0 -
PeopleSoft Sub-Total of Hardware, Software, Staffing, and Contingency |  |  |  |  | 1292041.832 | 3502114.3073 | 2614528.7594
Total Projected Cost by Implementation Phase: |  |  |  |  | 4789238.0577 | 6304736.3073 | 5655918.7594
Less Total Remaining Appropriation From MR#02043: |  |  |  |  | 554222
Total Projected Cost Less Total Remaining Appropriation: |  |  |  |  | 4235016.0577
Recommended Appropriations:
Designated Fund Balance for the E-Financial System implementation |  |  |  |  | 2895812
Designated Fund Balance for Data Privacy and Security |  |  |  |  | 1500000
Total Requested Appropriation: |  |  |  |  | 4395812
Plus Total Remaining Appropriation From MR#02043: |  |  |  |  | 554222
Total Projected Cost for Implementation Phase I: |  |  |  |  | 4950034

## Cost Summary
| Cost Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Total
Development Services:
| IT Hours - New Development, Phase I | Year 1: 255874.6667 | 255874.6667
| User Hours - PTNE/OT, Phase I | Year 1: 74038.4615 | 74038.4615
| Development Services Subtotal: | Year 1: 329913.1282 | 329913.1282 | 329913.1282
Hardware:
Hardware Subtotal:
Software:
Software Subtotal:
Infrastructure:
Infrastructure Subtotal
Training:
Training Subtotal:
Other:
| Other Subtotal: | 4459324.9295 | 6474927.9038 | 5656527.6231 | 468838.1265 | 516852.9371 | 542695.584 | 18119167.104
Costs Total: |  | 4789238.0577 | 6474927.9038 | 5656527.6231 | 468838.1265 | 516852.9371 | 542695.584 | 18449080.2322 | 18449080.2322

## Project Summary
| Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Total
Benefits/Savings:
| Tangible Benefits Subtotal: | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cost Avoidance Subtotal: | 1253200 | 339334.7865 | 2799856.7062 | 4116683.7553 | 5270007.9804 | 6865459.348 | 20644542.5764
| Annual Total Savings | 1253200 | 339334.7865 | 2799856.7062 | 4116683.7553 | 5270007.9804 | 6865459.348 | 20644542.5764 |  | 0
| Cumulative Total Savings | 1253200 | 1592534.7865 | 4392391.4927 | 8509075.248 | 13779083.2284 | 20644542.5764 | 20644542.5764 | 20644542.5764 | 0
Costs:
| Development Services Subtotal: | 329913.1282 | 0 | 0 | 0 | 0 | 0 | 329913.1282
| Hardware Subtotal: | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Software Subtotal: | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Infrastructure Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Training Subtotal: | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other Subtotal: | 4459324.9295 | 6474927.9038 | 5656527.6231 | 468838.1265 | 516852.9371 | 542695.584 | 18119167.104
| Annual Costs | 4789238.0577 | 6474927.9038 | 5656527.6231 | 468838.1265 | 516852.9371 | 542695.584 | 18449080.2322 |  | 0
| Cumulative Costs | 4789238.0577 | 11264165.9615 | 16920693.5846 | 17389531.7111 | 17906384.6482 | 18449080.2322 | 18449080.2322 | 18449080.2322 | 0
Statistics:
| Annual Return on Investment | -3536038.0577 | -6135593.1172 | -2856670.9169 | 3647845.6288 | 4753155.0433 | 6322763.764 | 2195462.3442
| Cumulative Return on Investment | -3536038.0577 | -9671631.1749 | -12528302.0919 | -8880456.4631 | -4127301.4198 | 2195462.3442 | 2195462.3442
| Annual Cost/Savings Ratio | 382.2% | 1908% | 202% | 11.39% | 9.807% | 7.905%
| Cumulative Cost/Savings Ratio | 382.2% | 707.3% | 385.2% | 204.4% | 130% | 89.37% | 89.37%
| Year Positive Payback Achieved | Year 6: Year 6 | Year 6
State or Federal Mandate?
Signatures:
| Project Sponsor | Year 1: Date:
| Information Technology Project Manager | Year 1: Date:
| Technical Services Manager | Year 1: Date:
#REF!
|  | 1 | 260 | 260
|  | 2 | 390 | 0 | 200
|  | 3 | 520 | 0
|  | 4 | 260 | 260
|  | 5 | 130 | 65
|  | 6 |  |  | 0
|  | 7 | 104 | 0
|  | 8 | 104 | 52
|  | 9 | 24 | 0 | 20
|  | 10 | 800 | 0
|  | 11 | 320 | 0
|  | 12 | 800 | 0
|  | 13 | 260 | 0
|  | 14 | 260 | 0
|  | 15 | 300 | 0
|  | 16 | 120 | 0 | 1500
|  | 17 | 3120 | 0
|  | 18 | 208 | 0
|  | 19 | 104 | 104
|  | 20 | 156 | 156
|  | 21 | 1.2 | 1.2
|  | 22 | 65 | 65
|  | 23 | 208 | 104
|  | 24 | 39.52 | 0
|  | 25 | 1.2 | 1.2
|  | 26 | 1300 | 0 | 234
|  |  | 9854.92 | 1068.4 | 1954
10.84%

## Assumptions
Date | Assumption Description